## Sheet1
Ashford Local Plan 2030 - Housing Trajectory (EXAMINATION - JUNE 2018) | TOTAL allocations Extant | UC 15/16 | 18/19 | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | 26/27 | 27/28 | 28/29 | 29/30 | TOTAL
TOWN CENTRE SITES
Former Powergen |  |  |  |  | 222 | 189 | 189 | 23/24: 60 | 660
Elwick Road Phase 2 | [5 empty] | 100 | 100 | [7 empty] | 200
Victoria Way East |  |  |  |  | 115 | 100 | [8 empty] | 215
Gasworks Lane (S10) | [7 empty] | 28/29: 75; 29/30: 75 | 150
Commercial Quarter (TC9 and S1) | 159 | [5 empty] | 79 | 23/24: 80 | 159
CHILMINGTON GREEN |  |  | 50 | 150 | 200 | 200 | 200 | 200 | 200 | 250 | 250 | 250 | 250 | 300 | 2500
URBAN SITES
Existing Allocations - Under construction
Finberry (LP 2000)* | 985 | 84 | 120 | 120 | 120 | 120 | 100 | 23/24: 65 | 645
Repton Park (LP 2000) | 475 | 74 | 100 | 100 | 104 | [9 empty] | 304
Godinton Way (TC8) | 83 |  |  | 28 | [10 empty] | 28
Blackwall Road (U5) |  |  | 2 | [11 empty] | 2
Existing allocations - Not started
Abbey Way (U1) |  |  |  | 23 | [10 empty] | 23
Lower Queens Road (U4 and S8) | [5 empty] | 40 | [8 empty] | 40
Former Ashford South Primary School (U6a and S13) | [5 empty] | 50 | 60 | [7 empty] | 110
K College, Jemmett Road (U6b and S12) |  |  | 50 | 50 | 60 | [9 empty] | 160
Leacon Road (U7 and S11) |  |  |  |  | 50 | 50 | [8 empty] | 100
Land at Butt Field Road, Singleton (U11) | 14 |  | 12 | [11 empty] | 12
Willesborough Lees (U14 and S17) |  |  | 20 | 60 | 60 | 60 | 20 | [7 empty] | 220
Conningbrook Phase 1 (U22) | 300 |  | 50 | 50 | 50 | 75 | 75 | [7 empty] | 300
Former Klondyke & Newtown Works Phase 2 (S6 and S7) |  |  |  |  | 93 |  |  | 50 | 50 | 50 | 50 | 50 | 50 |  | 393
New Urban Site allocations
Land NE of Willesborough Road, Kennington (S2) |  |  |  | 25 | 50 | 75 | 75 | 75 | 80 | 80 | 80 | 80 | 80 |  | 700
Court Lodge, Kingsnorth (S3) |  |  |  |  | 50 | 90 | 90 | 90 | 90 | 100 | 110 | 110 | 110 | 110 | 950
Land north of Steeds Lane and Magpie Hall Road (S4) |  |  |  |  | 50 | 60 | 60 | 23/24: 60; 24/25: 60; 25/26: 55; 26/27: 55 | 400
Land South of Pound Lane, Kingsnorth (S5) |  |  |  | 50 | 50 | 50 | [8 empty] | 150
Kennard Way - Henwood (S9) |  |  |  | 25 | [10 empty] | 25
Park Farm South East (S14) |  |  |  | 50 | 100 | 100 | 75 | [7 empty] | 325
Finberry North West (S15) | [7 empty] | 25/26: 75; 26/27: 75; 27/28: 75; 28/29: 75 | 300
Waterbrook (S16) |  |  |  | 20 | 50 | 50 | 50 | 23/24: 50; 24/25: 50; 25/26: 50; 26/27: 30 | 350
Conningbrook Residential Phase 2 (S19) | [7 empty] | 23/24: 70; 24/25: 50; 25/26: 50 | 170
Eureka Park (S20) |  |  |  | 50 | 80 | 80 | 80 | 23/24: 50; 24/25: 35 | 375
Land South of Brockmans Lane, Bridgefield (S45) | [6 empty] | 50 | 23/24: 50 | 100
Chart Road (S46) | [5 empty] | 25 | [8 empty] | 25
A20 CORRIDOR SITES (New allocations)
Land east of Hothfield Mill (S47) |  |  |  | 25 | 50 | [9 empty] | 75
Rear of Holiday Inn (S48) | [5 empty] | 50 | 50 | 23/24: 50 | 150
Land north of Tutt Hill (S49) |  |  |  |  | 25 | 50 | [8 empty] | 75
RURAL SITES
Existing Allocations - Under construction
TENT1A - Tenterden Southern Extension Phase A | 250 |  | 80 | 80 | 70 | [9 empty] | 230
Existing allocations & sites - Not Started
CHAR1 - Land South of Arthur Baker Playing Field, Charing (S29) |  |  | 51 | 40 | [10 empty] | 91
HAM2 - Land at Parker Farm, Hamstreet (S32) |  |  |  | 10 | [10 empty] | 10
ROLV1- Rolvenden Football Ground, Rolvenden | 40 |  | 30 | 10 | [10 empty] | 40
TENT1B - Tenterden Southern Extension Phase B (S24) | 175 |  |  |  |  | 70 | 80 | 23/24: 75 | 225
WOOD1 - Land at Front Rd, Woodchurch (S40) |  |  |  | 8 | [10 empty] | 8
WYE2 - Land at Luckly Field, Wye | 25 |  | 25 | [11 empty] | 25
Major Windfall - Tenterden, Tilden Gill** |  |  |  | 40 | 40 | 20 | [8 empty] | 100
New Rural Site Allocations
Aldington - Land north of Church View (S51) |  |  |  | 10 | [10 empty] | 10
Aldington - Land South of Goldwell Court (S52) |  |  |  |  | 10 | 10 | [8 empty] | 20
Appledore - The Street (S26) |  |  |  | 20 | [10 empty] | 20
Biddenden - North Street (S27) |  |  | 20 | 25 | [10 empty] | 45
Brook - Nats Lane (S53) |  |  |  | 10 | [10 empty] | 10
Challock - Land at Clockhouse (S54) |  |  | 15 | [11 empty] | 15
Charing - Northdown Service Station, Maidstone Road (S28) |  |  |  | 20 | [10 empty] | 20
Charing - Land Adjacent to Poppyfields (S55) |  |  |  | 30 | 75 | 75 | [8 empty] | 180
Chilham - Branch Road (S56) |  |  |  | 10 | [10 empty] | 10
Egerton - Land on New Road (S30) |  |  |  | 15 | [10 empty] | 15
Hamstreet - Land north of St. Mary's Close (S31) |  |  |  | 25 | 25 | 30 | [8 empty] | 80
Hamstreet - Warehorne Road (S57) |  |  |  | 25 | 25 | [9 empty] | 50
High Halden - Land at Hope House (S33) |  |  |  | 28 | [10 empty] | 28
High Halden - Stevenson Bros. A28 (S58) |  |  |  | 25 | 25 | [9 empty] | 50
Hothfield - Land East of Coach Drive (S34) |  |  |  |  | 20 | 20 | [8 empty] | 40
Mersham - Land at Old Rectory Close (S59) |  |  |  | 15 | [10 empty] | 15
Mersham - Land adjacent to Village Hall (S35) |  |  |  | 10 | [10 empty] | 10
Shadoxhurst - Land rear of Kings Head PH (S36) |  |  | 19 | [11 empty] | 19
Smarden - Land adjacent to Village Hall (S37) |  |  |  | 25 | 25 | [9 empty] | 50
Smeeth - Land South of Church Road (S38) |  |  |  | 20 | 15 | [9 empty] | 35
Tenterden ( St. Michaels) - Pope House Farm (S60) |  |  |  | 25 | 25 | [9 empty] | 50
Wittersham - Land between Lloyds Green and Jubilee Fields (S61) |  |  |  | 20 | 20 | [9 empty] | 40
Woodchurch - Land off Appledore Road (S62) |  |  |  | 15 | 15 | [9 empty] | 30
NEIGHBOURHOOD PLANS
WYE3, Former Imperial College | 52 |  |  | 40 |  | 40 | 45 | [7 empty] | 125
Bethersden Neighbourhood Plan area |  |  |  | 20 | 14 | [9 empty] | 34
Pluckley Neighbourhood Plan area |  |  | 25 | 8 | [10 empty] | 33
Rolvenden Neighbourhood Plan area |  |  |  | 10 | 14 | [9 empty] | 24
WINDFALLS (NON ALLOCATED SITES)
Windfalls - Small sites (Under 10 dwellings) - not started*** | 257 |  |  | 102 | 102 | 102 | [8 empty] | 306
Windfalls - Small sites (Under 10 dwellings) - under construction | 127 | 127 | 140 | [11 empty] | 140
Windfalls - Major sites (10 dwellings or above) - not started*** | 96 |  |  | 20 | 23 | 22 | [8 empty] | 65
Windfalls - Major sites (10 dwellings or above) - under construction | 64 | 64 | 209 | 55 | [10 empty] | 264
Projected Future windfalls (Based on assumption from past delivery) | [6 empty] | 150 | 150 | 150 | 150 | 100 | 100 | 100 | 100 | 1000
ANNUAL TOTAL |  | 349 | 1018 | 1642 | 2122 | 2003 | 1628 | 1175 | 765 | 860 | 750 | 665 | 740 | 585 | 13953
CUMULATIVE TOTAL |  |  | 1018 | 2660 | 4782 | 6785 | 8413 | 9588 | 10353 | 11213 | 11963 | 12628 | 13368 | 13953
LP 2000 = Ashford Borough Local Plan 2000 Site policy *Reduced to take account of 90 live/work units not being built. **Not counted in major windfall figures below. ***Extant permissions not started have been reduced by 25% for assumed non delivery | bar: 23/24 to 24/25